## Slide 1: THE ZERO SHUTDOWN GOAL
Rich Tree
Vice President, North America
CAI

## Slide 2: Rethinking the frequency and execution of planned shutdowns

## Slide 3
Welcome & Introductory Remarks
Shutdown Drivers – The Problem with Shutdowns
Condition Based Maintenance – Maintenance Optimization
Shutdown Optimization – Driving to Zero
Question & Answer
Agenda

## Slide 4
Shutdowns represent the greatest negative contribution to overall equipment effectiveness (OEE) across all process industries and introduces new and significant risk that must be managed by the operations managers.
There are few activities on the maintenance calendar that pose a bigger risk to your production than shutdowns. They consume resources, create downtime, and are often plagued by over-runs and restart issues.
Introduction

## Slide 5
Shutdown Illustrated
How much does an hour of downtime cost your company in lost revenue?

## Slide 6
Traditionally calculated as a direct cost
Occasionally idled labor force can be absorbed
True cost is lost Opportunity
Especially true for Constrained products
With Flexible manufacturing-lost opportunities
Calculate this number- Dwarfs direct cost
$1B Facility- $5M/day lost revenue
Talk to production managers!
The Real cost of Shutdowns

## Slide 7
Preventive Maintenance
    Beneficial
    Unnecessary
Preventive maintenance driven by pure water system cleanliness
    Overly conservative
Planned Corrective Maintenance
Capital Projects
Fear?
Shutdown Drivers
Notes: Lou

## Slide 8
Lost Production/Lost Revenue
Durations not Restrained
  S/D go for Weeks/Months
Relied Upon
Disruptive to Operations Flow
Infant Mortality Failures
HR Challenge
Encourages Poor Planning & Scheduling
The Problems with Shutdowns
Notes: Lou

## Slide 9
Routine elastomer replacements
Mechanical seal replacements
Heat exchanger pressure tests
Routine Derouging/Passivation
AHU pre-filters/belts
Cleanroom/HEPA Testing
Is it possible these are all driven by overly conservative thinking? Can we use risk-based decision making
Common Industry Maintenance Practices
Cleanliness Driven
Notes: Rich

## Slide 10
Elastomer Change out Periods based on Company
2011 BioForum Operation Group non-scientific survey of their membership
Notes: Rich

## Slide 11
Biases
    Anchoring
    Availability
    Substitution
    Framing
1978 Nolan and Heap published a report for United Airlines. The report contained information on the conditional probability of failure against operating age for a variety of electrical and mechanical items in the aviation industry.
The most interesting Nolan and Heap finding was that 68% of items conformed to the failure pattern classified as the Infant Mortality Failure Pattern.
What Drives the Decision Making Process? Heuristics/Biases.
Notes: Rich

## Slide 12
Failure Profiles
UAL 1968 | BROBERG 1973 | MSDP 1982 | SSMD 1993 | SUBMEP 2001
4% | 3% | 3% | 6% | 2%
2% | 1% | 17% |  | 10%
5% | 4% | 3% |  | 17%
7% | 11% | 6% |  | 9%
14% | 15% | 42% | 60% | 56%
68% | 66% | 29% | 33% | 6%
89% | 92% | 77% | 93% | 
Notes: Rich

## Slide 13
Scheduled intrusive maintenance can actually increase overall failure rates by introducing infant mortality into otherwise stable systems.
The increased conditional probability of failure after maintenance is a result of such factors as human error, the use of defective material, errors in technical documentation, etc.
    Anyone ever experience a diaphragm replacement that leaks after the maintenance where otherwise would never have leaked before?
If the maintenance were not mandated, there would not be the exposure to infant mortality and no penalty in decreased operational availability would result.
Early Failures (F) – Why So High?
Notes: Rich

## Slide 14: Maintenance Strategies
Rethinking the approach
Notes: Rich

## Slide 15
Up to 40% of all preventive maintenance tasks originate from diaphragm valve maintenance
    Improving reliance on condition based maintenance
    Reconsidering the risk of elastomer replacements
Testing HEPA filters and clean rooms – evaluate practices using the December 2015 update to ISO 14644-2
    Reconsider the risk based on the newest revision to the specifications for testing and monitoring to prove continued compliance
Challenge the Assumptions
Notes: Rich

## Slide 16: Planning & Scheduling Strategies
Rethinking the approach

## Slide 17: Normal Planning & Scheduling
Planned Maintenance Outages
Downtime (Planned Or Unplanned)
Notes: Rich

## Slide 18: Optimized Planning & Scheduling
Planned Maintenance Outages
Downtime (Planned Or Unplanned)
Available downtime is used to complete shutdown driving maintenance
Planned Maintenance Outages once every three years instead
Notes: Rich

## Slide 19: Shutdown Optimization Strategies
Notes: Lou

## Slide 20: Shutdown Optimization
Ensure your entire organization understands your definition for a shutdown period.
Establish clear roles and responsibilities for shutdowns.
Manage a shutdown like a project.
Plan, plan and plan; then work the plan. Establish a planning process. Plan for restart and recovery.
Keep leadership involved.
Conduct & implement Lessons Learned
Notes: When you state “Shutdown” does everyone understand it includes the ramp down and ramp up periods or are they thinking about the actual work period? This impacts everyone from the facility to inventory and sales.
Clear roles and responsibilities ensure every task or need is assigned to someone and that someone understands they own it.
A shutdown has to be managed like a project. There has to be a defined period and a defined budget with well managed work scope. Work scope needs to be frozen at a specific point prior to the shutdown and any addition after that point needs to be managed to understand additional cost, manpower and schedule impact.
There has to be an overall shutdown coordinator that has responsibility for planning of the shutdown and does not just start when the shutdown starts. For some facilities this may be a full time, year-round position. Smaller facilities may only require someone part-time. Every bit of work to be executed during the shutdown needs to go into the overall shutdown plan. Plan all retests and validation efforts into the plan.
A planning process involves representatives from every department (Maintenance, Planning, Engineering, Quality, Validation, Lab, EH&S and Leadership). This way, there are no surprises that are likely to arise because someone did not understand a requirement. An example may be Environmental may need to complete a new permit due to a change in emission controls. Utilize personnel from Production to assist with work, if available. Work around the clock instead of just during day shift. Paying additional OT is often a drop in the bucket when it comes to increasing days of a shutdown.
Plant leadership must remain involved in the shutdown. Ensure frequent walkdowns by leadership to ensure all work is being conducted to standard. Have daily EH&S walkdowns.
Ensure the restart and recovery of critical utilities is integrated into the shutdown as well as time for cleaning and restoration of environmental conditions. Utilities (pure water, steam, WFI, waste treatment) & HVAC need to be coordinated for restart and environmental monitoring to restore systems and spaces.
Always conduct a lessons learned from every shutdown and implement those into your next shutdown planning and execution process.

## Slide 21: Shutdown Optimization
Analyze current drivers
    Can you do it in smaller parts?
    Can you modify system to allow partial SD?
      N+1
      Add valves, temporary system tie ins
    Validate alternative sanitizations
    Calibrations
  Increase periodicity
  Add dry wells and isolation valves

## Slide 22: Example
WFI system
    Inline TOC and Conductivity - release on these
    Validate pump sanitization
    Revise calibration PM for level, pressure
    Remove calibration of non-critical instruments
    Go to trace metal for derouge
    Use the available downtime for elastomers. Should have several systems

## Slide 23: Helpful hints
24x7 usually cheaper then lost production
Write contracts with schedule clauses
Detailed restart plan
    Risk based sampling
    Risk based use of systems
    Start utilities while construction finishes.

## Slide 24: Question & Answer